HANGA WORKS

2-Week Sprint Plan  —  v2.0  (Updated)

Phase 1  ·  4 Developers  ·  Node.js · React · PostgreSQL · GitHub · Render · Vercel

# 1. Technology Stack

| Layer | Technology | Details & Rationale |
| --- | --- | --- |
| Frontend | React 18 + TypeScript | Vite build tool, React Router v6, TanStack Query, Tailwind CSS. Deployed to Vercel with automatic preview per PR. |
| Backend API | Node.js + NestJS + TypeScript | NestJS modular architecture with decorators, DI, and Guards for RBAC. OpenAPI/Swagger docs. REST at /api/v1/. |
| Database | Prisma + PostgreSQL | Prisma schema as single source of truth. Migrations via prisma migrate. Hosted PostgreSQL on Render. |
| Auth | JWT + Passport.js | passport-jwt strategy. Access tokens 15 min, refresh tokens 7 days in httpOnly cookies. RBAC Guards. |
| Cache | Redis (ioredis) | Session management, rate limiting, course listing cache, notification queues. |
| Real-time | Socket.io | WebSocket server on NestJS. socket.io-client on React for live notifications and status updates. |
| Storage | S3 / Cloudflare R2 | Certificate PDFs, course media, profile photos. Presigned URLs for secure upload. |
| Email | SendGrid | Transactional emails: registration, application updates, course completion, cert issued. |
| CI/CD | GitHub Actions | On PR: tsc, eslint, jest. On merge to main: auto-deploy to Render (API) and Vercel (Web). |

# 2. Repository & Project Structure

Two separate GitHub repositories under the team organisation:

| hanga-works-backend (NestJS / Render) | hanga-works-frontend (React / Vercel) |
| --- | --- |
| src/auth/ ← JWT, Passport, Guards src/users/ ← User module + RBAC src/lms/ ← Courses, Progress, Quiz src/jobs/ ← Listings, Applications src/certifications/ ← Issue, Verify, PDF src/notifications/ ← SendGrid, Socket.io src/employer/ ← ATS, Dashboard src/analytics/ ← Metrics endpoints src/prisma/ ← Prisma service src/redis/ ← Redis service src/common/ ← Filters, Pipes prisma/schema.prisma prisma/seed.ts .env.example | src/components/ui/ ← Shared UI components src/components/layout/ ← Sidebar, Topbar src/components/shared/ ← ProgressBar, Avatar src/pages/auth/ ← Login, Register src/pages/dashboard/ ← Dashboard src/pages/courses/ ← CourseList, Detail src/pages/jobs/ ← JobList, Apply src/pages/profile/ ← Profile page src/pages/employer/ ← Employer pages src/features/ ← Feature hooks src/services/ ← API service layer src/types/ ← TypeScript types src/utils/ ← Helper functions .env.example |

# 3. Updated Team Assignments

Roles have been updated from the original sprint plan v1.1:

| YVES Backend Developer • Prisma schema & seed data • LMS module (courses, progress, quiz) • Jobs marketplace API • Certifications module • Analytics & job matching • Redis caching (ioredis) • Swagger / OpenAPI docs | LEON Backend Developer • NestJS scaffold & setup • JWT / Passport auth + RBAC • Notifications (SendGrid + Socket.io) • Employer ATS module • Security hardening • Production deploy (Render) • Database migrations | ROSINE Frontend Developer • UI template & design reference • Auth screens (login, register) • LMS UI (courses, progress) • Job marketplace UI • Skill profile UI • UI polish & mobile responsive • Accessibility (WCAG 2.1 AA) | BLAISE Frontend Developer • React scaffold + Tailwind setup • Dashboard layout + sidebar nav • GitHub Actions CI/CD • Employer dashboard + ATS kanban • Admin panel • Lighthouse performance audit • Vercel production deploy |
| --- | --- | --- | --- |

# 4. Week 1 — Foundation & Design (Days 1–5)

## Day 1 — Kickoff & Scaffold

| Day 1 | ALL | [MEETING] Project kickoff (2 hours — all hands) Align on SRS Phase 1 scope and folder structure Agree on TypeScript strict mode, ESLint/Prettier config Confirm Git branching strategy: feature/task-name → develop → main Set daily standup cadence (15 min) Each person confirms their Day 1 task is clear |
| --- | --- | --- |

| Day 1 | LEON | [DEV] NestJS scaffold + full project structure Run: npx @nestjs/cli new hanga-works-backend --strict Create ALL folders and empty placeholder files per agreed structure Set up .env file with all required variables Connect Prisma to PostgreSQL Push to GitHub main branch + create develop branch Add branch protection rules on main |
| --- | --- | --- |

| Day 1 | YVES | [DEV] Prisma schema + seed data Define all models: User, Course, Module, Enrollment, Progress Define: Job, Application, Certificate, SkillTag models Set up all relations between models Write seed.ts: 20 learners, 5 employers, 10 courses, 20 jobs Run: npx prisma migrate dev --name init Verify with: npx prisma studio |
| --- | --- | --- |

| Day 1 | BLAISE | [DEV] React scaffold + Tailwind + routing Run: npm create vite@latest hanga-works-frontend -- --template react-ts Install: tailwindcss, react-router-dom, @tanstack/react-query, axios Install: socket.io-client Set up all routes in App.tsx Create src/services/api.ts (axios instance) Push to GitHub + link repo to Vercel |
| --- | --- | --- |

| Day 1 | ROSINE | [DESIGN] Find UI template + design reference Go to figma.com/community Search: job board dashboard or LMS dashboard Duplicate a free template to team Figma Share Figma link + template URL with team on WhatsApp No need to design from scratch — use existing template |
| --- | --- | --- |

## Days 2–3 — Auth, LMS API & CI/CD

| Day 2-3 | LEON | [DEV] Auth module — JWT + Passport + RBAC Files: src/auth/auth.module.ts, auth.controller.ts, auth.service.ts Files: src/auth/strategies/jwt.strategy.ts Files: src/auth/guards/jwt-auth.guard.ts, roles.guard.ts Files: src/auth/decorators/roles.decorator.ts Files: src/auth/dto/register.dto.ts, login.dto.ts Endpoints: POST /auth/register, /login, /refresh, /logout Access token: 15 min ¦ Refresh token: 7 days httpOnly cookie |
| --- | --- | --- |

| Day 2-3 | YVES | [DEV] LMS NestJS module — courses, enrollment, progress Files: src/lms/courses/, src/lms/enrollment/, src/lms/progress/ Endpoints: GET /courses, GET /courses/:id Endpoints: POST /enrollments, PATCH /progress/:moduleId Endpoints: POST /quiz/:id/submit Redis cache for course listing (TTL 5 min) Write Jest unit tests Branch: feature/lms-module |
| --- | --- | --- |

| Day 2-3 | ROSINE | [DEV] Auth screens + dashboard shell (React) Files: src/pages/auth/Login.tsx, Register.tsx, VerifyEmail.tsx Files: src/features/auth/useAuth.ts Files: src/services/auth.service.ts Protected routes with auth context (React Router v6) Connect to Leon's auth API endpoints Branch: feature/auth-pages |
| --- | --- | --- |

| Day 2-3 | BLAISE | [DEV] Dashboard layout + sidebar nav Files: src/components/layout/Sidebar.tsx, Topbar.tsx, DashboardLayout.tsx Files: src/components/ui/Button.tsx, Input.tsx, Card.tsx, Badge.tsx Files: src/components/shared/NotificationBell.tsx, Avatar.tsx Files: src/pages/dashboard/Dashboard.tsx TanStack Query setup + axios instance Branch: feature/dashboard-layout |
| --- | --- | --- |

## Day 4 — Mid-Sprint Sync & Features

| Day 4 | ALL | [MEETING] Mid-sprint sync (1 hour) Review Swagger UI at /api/docs Finalise request/response shapes for Job and LMS endpoints Rosine demos React screens on Vercel preview URL Identify and resolve any blockers |
| --- | --- | --- |

| Day 4 | YVES | [DEV] Jobs marketplace API Files: src/jobs/jobs.module.ts, jobs.controller.ts, jobs.service.ts Files: src/jobs/dto/create-job.dto.ts, apply-job.dto.ts Endpoints: POST /jobs, GET /jobs (filters), GET /jobs/:id Endpoints: POST /jobs/:id/apply, PATCH /applications/:id/status DTOs with class-validator Branch: feature/jobs-api |
| --- | --- | --- |

| Day 4 | LEON | [DEV] Notifications — SendGrid + Socket.io Files: src/notifications/notifications.module.ts Files: src/notifications/notifications.gateway.ts Files: src/notifications/notifications.service.ts SendGrid: registration, application update, course complete, cert issued Socket.io events: job-match, application-status, course-complete Branch: feature/notifications |
| --- | --- | --- |

| Day 4 | ROSINE | [DEV] LMS UI — course browser + progress Files: src/pages/courses/CourseList.tsx, CourseDetail.tsx Files: src/components/shared/ProgressBar.tsx Files: src/features/lms/useCourses.ts, useProgress.ts Connect to Yves's LMS API endpoints Branch: feature/lms-ui |
| --- | --- | --- |

| Day 4 | BLAISE | [DEV] GitHub Actions CI/CD + Vercel File: .github/workflows/ci.yml On PR: run tsc --noEmit and eslint On merge to main: Vercel auto-deploys Set VITE_API_URL in Vercel dashboard Branch protection rules on main confirmed Branch: feature/cicd |
| --- | --- | --- |

## Day 5 — Week 1 Wrap & Staging Deploy

| Day 5 | ALL | [REVIEW] PR reviews + integration merge + staging deploy All feature branches open PRs to develop CI must pass (tsc, eslint, jest) + 1 approving review Merge to develop → auto-deploy to Render staging + Vercel preview Smoke test: register → login → enrol course → job browse |
| --- | --- | --- |

| Day 5 | ALL | [MEETING] Week 1 retro + Week 2 planning (1 hour) Demo on Vercel preview and Render staging URLs Velocity check vs plan — reprioritise if needed Confirm Week 2 task assignments Update Trello board |
| --- | --- | --- |

✓ Week 1 Milestone — Auth API live on Render staging · LMS + Jobs API on Swagger · React app on Vercel preview · GitHub Actions CI green

# 5. Week 2 — Features, Polish & Deploy (Days 6–10)

## Day 6 — Certifications & Marketplace UI

| Day 6 | YVES | [DEV] Certifications module — PDF + S3 Files: src/certifications/certifications.module.ts Files: src/certifications/certifications.controller.ts Files: src/certifications/certifications.service.ts Auto-trigger on course completion (NestJS EventEmitter) Generate PDF with pdfkit, upload to Cloudflare R2 / AWS S3 GET /certificates/verify/:token (public) POST /certificates/validate (employer-facing) Branch: feature/certifications |
| --- | --- | --- |

| Day 6 | LEON | [DEV] Employer ATS module — pipeline stages Files: src/employer/employer.module.ts Files: src/employer/employer.controller.ts, employer.service.ts Files: src/employer/dto/update-stage.dto.ts Endpoints: POST /employer/jobs, GET /employer/jobs/:id/applicants Endpoints: PATCH /employer/applications/:id/stage Stages: applied → reviewing → shortlisted → hired/rejected Protected by @Roles('EMPLOYER') guard Branch: feature/employer-ats |
| --- | --- | --- |

| Day 6 | ROSINE | [DEV] Job marketplace UI Files: src/pages/jobs/JobList.tsx, JobDetail.tsx, MyApplications.tsx Files: src/services/jobs.service.ts, src/types/job.types.ts Files: src/features/jobs/useJobs.ts, useApplications.ts Job listing with filters, one-click apply Application status: Applied, Reviewing, Shortlisted, Hired, Rejected Branch: feature/jobs-ui |
| --- | --- | --- |

| Day 6 | BLAISE | [DEV] Employer dashboard + ATS kanban Files: src/pages/employer/EmployerDashboard.tsx Files: src/pages/employer/PostJob.tsx, Applicants.tsx Files: src/components/ui/Modal.tsx Kanban board: Applied → Reviewing → Shortlisted → Hired Candidate profile modal/drawer Protected: EMPLOYER role only Branch: feature/employer-ui |
| --- | --- | --- |

## Days 7–8 — Analytics, Profiles & Admin

| Day 7-8 | YVES | [DEV] Analytics endpoints + job matching score Files: src/analytics/analytics.module.ts Files: src/analytics/analytics.controller.ts, analytics.service.ts GET /analytics/overview — DAU, MAU, completion rate GET /jobs/recommended — match user skills to jobs, return top 10 GET /analytics/export?format=csv Branch: feature/analytics |
| --- | --- | --- |

| Day 7-8 | ROSINE | [DEV] Skill profile UI + UI polish Files: src/pages/profile/Profile.tsx Files: src/utils/formatDate.ts, formatCurrency.ts Skill tags with proficiency selector Certificate badges display Empty state screens for no jobs / no courses Loading skeleton screens Mobile responsive check on all pages Branch: feature/profile-ui |
| --- | --- | --- |

| Day 7-8 | BLAISE | [DEV] Admin panel + hooks Files: src/pages/admin/AdminPanel.tsx Files: src/hooks/useLocalStorage.ts, useSocket.ts User list with account actions Platform stats cards Content moderation queue Branch: feature/admin-panel |
| --- | --- | --- |

## Day 9 — QA, Security & Performance

| Day 9 | ALL | [REVIEW] Full QA pass — all flows end-to-end on staging Test: register → login → enrol course → complete → cert issued Test: apply to job → employer sees applicant in ATS Test on mobile viewport (Chrome DevTools) Log bugs in GitHub Issues with severity labels |
| --- | --- | --- |

| Day 9 | LEON | [DEV] Security hardening Files: src/common/filters/http-exception.filter.ts Files: src/common/interceptors/response.interceptor.ts Files: src/common/pipes/validation.pipe.ts Add helmet middleware (HTTP security headers) Add @nestjs/throttler rate limiting: 100 req/15 min Verify no secrets in GitHub codebase (git grep) Branch: feature/security |
| --- | --- | --- |

| Day 9 | BLAISE | [DEV] Performance audit Lighthouse audit on Vercel preview (target: Performance > 90) Code-split heavy routes with React.lazy() Verify WebSocket reconnection logic Accessibility check with Axe |
| --- | --- | --- |

## Day 10 — Production Deploy & Demo

| Day 10 | LEON | [DEVOPS] Production deployment — Render Merge develop → main (CI green + 2 approvals) Set all env vars in Render dashboard Run: npx prisma migrate deploy on production DB Verify HTTPS on Render URL Confirm daily DB backup active |
| --- | --- | --- |

| Day 10 | BLAISE | [DEVOPS] Production deployment — Vercel Vercel auto-deploys from main branch Set all production env vars in Vercel dashboard Confirm frontend connects to Render API Final mobile sweep |
| --- | --- | --- |

| Day 10 | ALL | [MEETING] Final demo & handoff presentation (2 hours) Yves: API demo via Swagger UI Leon: Auth flow + security + Render deployment overview Rosine: Full UI walkthrough on Vercel production URL Blaise: CI/CD pipeline + employer dashboard demo Write README.md for both repos Document Phase 2 backlog in GitHub Issues |
| --- | --- | --- |

✓ Week 2 Milestone — HANGA WORKS Phase 1 LIVE: API on Render · Frontend on Vercel · PostgreSQL migrated · CI/CD green · All features shipped

# 6. CI/CD Pipeline Summary

| 1. Developer pushes feature branch | → | 2. GitHub Actions runs tsc · eslint · jest | → | 3. PR opened + 1 approving review | → | 4. Merge to main → Auto-deploy |
| --- | --- | --- | --- | --- | --- | --- |

Environment variables are never committed to GitHub. Set in Render dashboard (API) and Vercel dashboard (Web) only.

# 7. Non-Functional Requirements

| Category | Requirement | Target | How We Meet It |
| --- | --- | --- | --- |
| Performance | Page load (P95) | < 2 seconds | Vercel CDN + Vite code-splitting + React.lazy() |
| Performance | API response | < 500ms | Redis cache + Prisma connection pool |
| Performance | WebSocket latency | < 1 second | Socket.io on Render (same region as DB) |
| Security | Data in transit | TLS 1.2+ | Render + Vercel enforce HTTPS automatically |
| Security | Auth | JWT + refresh | Passport.js strategy, httpOnly cookies |
| Security | Input validation | All endpoints | class-validator on all DTOs |
| Scalability | Concurrent users | 10,000+ | Stateless NestJS + Render autoscale |
| Reliability | Uptime SLA | 99.5% | Render managed infra + daily PG backups |
| Usability | Onboarding | < 5 min | 3-step wizard, < 5 form fields per step |
| Usability | Accessibility | WCAG 2.1 AA | Tailwind a11y utilities + Axe CI scan |

# 8. Sprint KPIs

| 30+ API endpoints (Swagger) | 15+ React pages / routes | 2 GitHub Actions workflows | 90+ Target Lighthouse score |
| --- | --- | --- | --- |

© 2026 HANGA WORKS. All rights reserved.  —  Sprint Plan v2.0 (Updated)